## Reqs
Req | Description
4.1.12 | 4.1.12 The system shall enable registered users to login to using a valid username and password. . The username should be in an email address format and password must be a minimum length six characters.

## Test Conditions
Test Condition ID | Description | Source | Priority
Manage_TConn_1 | To show that the manage account page has the conpany logo in the header on the page. | Requirements 4.1.1 | Low | What is a test condition?
Manage _TConn_1 | To show that a footer with the copyright and site version information is available on the page | Requirements 4.1.2 | Low
Manage_TConn_2 | To show that all user inputs parts of the website have appropriate validation | Requirements 4.1.3 | Medium | •A statement of something we want to test.
•The required behaviour of the system when that item is used or performed.
•They enable us to render the requirements and other oracles in such a form that we can understand them and begin to think about how we’re going to test them.
Test Condition:
“An item or event of a component or system that could be verified by one or more test cases, e.g. a function, transaction, feature, quality attribute, or structural element.”
Note on B1: qubsys: Start with : “To show that…” Split the test condition into two parts: “When I do this…this happens…”.

## Test Cases
Test case ID | Objective | Preconditions | Test data | Test condition(s) | Priority | Test completion date | Status | Tester | Defect ID | Defect Status | Defect Severity | Open Date | Close Date | Description / Comment
Manage_TCase_1 | Check if the Company Logo is present in the header of the page | On the Manage Account page | N/A | Manage_TConn_1 | Low | 2015-03-12 | Passed | Chris McClune | [6 empty] | Test Case:
Manage_TCase_2 | Check if the Copyright and site version is available in the footer of the page | On the Manage Account page | N/A | Manage_TConn_2 | Low | 2015-03-12 | Failed | Chris McClune | Manage_1 | Open | Minor | 2015-03-12 |  | The footer does not contain either the site version or the copyright information |  | “A set of input values, execution pre-conditions, expected results and execution post-conditions, developed for a particular objective or test condition, such as to exercise a particular program path or to verify compliance with a specific requirement.”
Manage_TCase_3 | Check if user input parts of the site have appropriate validation | On the Manage Account page | email: cmcclune02@qub.ac.uk username: chris | Manage_TConn_3 | Medium | 2015-03-12 | Failed | Chris McClune | Manage_2 | Open | Major | 2015-03-12 |  | A password of less that 7 characters can be used, when explicity says 7 or over. |  |  |  | [ISTQB Glossary]
Stats on Test case runs
[16 empty] | Passed | 1
[16 empty] | Failed | 2
[16 empty] | Not execited | 0
Stats on Defects
[16 empty] | Minor | 1
[16 empty] | Moderate | 0
[16 empty] | Major | 1
[16 empty] | Critical | 0
[16 empty] | Cosmetic | 0
Note on A1: qubsys: A unique Identifier for thr Test case
Note on H1: qubsys: The status of the Test case i.e. is it not executed, passed or failed
Note on J1: qubsys: A unique incident ID
Note on K1: qubsys: The status of the defect - initially open but may be moved to reject on review or closed when defect is fixed
Note on L1: qubsys: The assigned severity - Critical: The defect that results in the termination of the complete system or one or more component of the system and causes extensive corruption of the data. The failed function is unusable and there is no acceptable alternative method to achieve the required results then the severity will be stated as critical. Major: The defect that results in the termination of the complete system or one or more component of the system and causes extensive corruption of the data. The failed function is unusable but there exists an acceptable alternative method to achieve the required results then the severity will be stated as major. Moderate: The defect that does not result in the termination, but causes the system to produce incorrect, incomplete or inconsistent results then the severity will be stated as moderate. Minor: The defect that does not result in the termination and does not damage the usability of the system and the desired results can be easily obtained by working around the defects then the severity is stated as minor. Cosmetic: The defect that is related to the enhancement of the system where the changes are related to the look and field of the application then the severity is stated as cosmetic.

## Test Procedures
Test Procedure ID | Test Case ID | Description | Expected Result | Comments | Test Procedure Specification:
Manage_Tproc_1 | Manage_TCase_1 | Go to manage account page and check for the company logo in the header | Company Logo appears in header | N/A |  | “A document specifying a sequence of actions for the execution of a test. Also known as test script or manual test script.”
Manage_Tproc_2 | Manage_TCase_2 | Go to manage account page and check for the copyright and version details in the footer | Should see the details in the footer | N/A
Manage_Tproc_3 | Manage_TCase_3 | Go to manage account page and change password to something with less than 7 characters | Should not be allowed to change password to this and error message should appear | When the password is changed the prompt says that the username has been changed.

## Settings
Test status | Test priority | Defect status | Defect Priority
Not executed | High | Closed | Minor
Passed | Medium | Open | Moderate
Failed | Low | Rejected | Major
Critical
Cosmetic