## Reqs
Req | Description
4.1.12 | 4.1.12 The system shall enable registered users to login to using a valid username and password. . The username should be in an email address format and password must be a minimum length six characters.

## Test Conditions
Test Condition ID | Description | Source | Priority
Manage_TConn_1 | To show that the manage account page has the conpany logo in the header on the page. | Requirements 4.1.1 | Low | What is a test condition?
Manage_TConn_2 | To show that a footer with the copyright and site version information is available on the page | Requirements 4.1.2 | Low
Manage_TConn_3 | To show that all user inputs parts of the website have appropriate validation | Requirements 4.1.3 | Medium | •A statement of something we want to test.
Manage_TConn_4 | To show that the manage account page has a title | Requirements 4.1.4 | Low | •The required behaviour of the system when that item is used or performed.
Manage_TConn_5 | To show that the system has a functional 'My account' Page | Requirements 4.1.5 | High | •They enable us to render the requirements and other oracles in such a form that we can understand them and begin to think about how we’re going to test them.
Manage_TConn_6 | To show that the manage account page has a common navigation area | Requirements 4.1.7 | Medium | Test Condition:
Manage_TConn_7 | To show that from the manage account page the user can successfully navigate to the Home, Order, About and Contact pages | Requirements 4.1.8 | High |  | “An item or event of a component or system that could be verified by one or more test cases, e.g. a function, transaction, feature, quality attribute, or structural element.”
Manage_TConn_8 | To show that a logged in user can direct to the manage account page - reset password. In addition all logged in users should be able to log off from the manage account page | Requriements 4.1.10 | High
Manage_TConn_9 | To show that from the My Account - reset password page that a user is able to reset his/her password by entering the current password, the new password and the confirmation of the new password | Requirements 4.1.35 | High
Manage_TConn_10 | To show that an appropriate message is displayed when the password is changed. | Requirements 4.1.35 | High
Manage_TConn_11 | To show that there is appropriate validation on size and type of password used in registration is used on the manage account page | Requirements 4.1.35 | High
Manage_TConn_12 | To check the Manage account - reset password page loads correctly on the target mobile device: Amazon Kindle Fire 7 inch. | Requirements 3.2.2 | High
Manage_TConn_13 | On the Amazon Kindle Fire 7 inch mobile device, the user is able to reset his/her password by entering the current password, the new password and the confirmation of the new password | Requirements 3.2.2 | High
Manage_TConn_14 | On the Amazon Kindle Fire 7 inch mobile device, that an appropriate message is displayed when the password is changed. | Requirements 3.2.2 | Medium
Manage_TConn_15 | On the Amazon Kindle Fire 7 inch mobile device, that there is appropriate validation on size and type of password used in registration is used on the manage account page | Requirements 3.2.2 | High
Manage_TConn_16 | To check the Manage account - reset password page loads correctly on the target mobile device: iPad 4. | Requirements 3.2.2 | High
Manage_TConn_17 | On the iPad 4 mobile device, the user is able to reset his/her password by entering the current password, the new password and the confirmation of the new password | Requirements 3.2.2 | High
Manage_TConn_18 | On the iPad 4 mobile device, that an appropriate message is displayed when the password is changed. | Requirements 3.2.2 | Medium
Manage_TConn_19 | On the iPad 4 mobile device, that there is appropriate validation on size and type of password used in registration is used on the manage account page | Requirements 3.2.2 | High
Manage_TConn_20 | To check the Manage account - reset password page loads correctly on the target mobile device: iPhone 6. | Requirements 3.2.2 | High
Manage_TConn_21 | On the iPhone 6 mobile device, the user is able to reset his/her password by entering the current password, the new password and the confirmation of the new password | Requirements 3.2.2 | High
Manage_TConn_22 | On the iPhone 6 mobile device, that an appropriate message is displayed when the password is changed. | Requirements 3.2.2 | Medium
Manage_TConn_23 | On the iPhone 6 mobile device, that there is appropriate validation on size and type of password used in registration is used on the manage account page | Requirements 3.2.2 | High
Manage_TConn_24 | To check the Manage account - reset password page loads correctly on the target mobile device: Google Nexus 10. | Requirements 3.2.2 | High
Manage_TConn_25 | On the Google Nexus 10 mobile device, the user is able to reset his/her password by entering the current password, the new password and the confirmation of the new password | Requirements 3.2.2 | High
Manage_TConn_26 | On the Google Nexus 10 mobile device, that an appropriate message is displayed when the password is changed. | Requirements 3.2.2 | Medium
Manage_TConn_27 | On the Google Nexus 10 mobile device, that there is appropriate validation on size and type of password used in registration is used on the manage account page | Requirements 3.2.2 | High
Manage_TConn_28 | To check the Manage account - reset password page loads correctly on the target mobile device: Samaung Galaxy S4. | Requirements 3.2.2 | High
Manage_TConn_29 | On the Samsung galaxy S4 mobile device, the user is able to reset his/her password by entering the current password, the new password and the confirmation of the new password | Requirements 3.2.2 | High
Manage_TConn_30 | On the Samsung galaxy S4 mobile device, that an appropriate message is displayed when the password is changed. | Requirements 3.2.2 | Medium
Manage_TConn_31 | On the Samsung galaxy S4 mobile device, that there is appropriate validation on size and type of password used in registration is used on the manage account page | Requirements 3.2.2 | High
Manage_TConn_32 | On the Amazon Kindle Fire 7 inch mobile device, the Manage account - reset password page should have a copyright and site version in the footer | Requirements 4.1.2 | Low
Manage_TConn_33 | On the Amazon Kindle Fire 7 inch mobile device, to ensure that logged users can log off from the Manage account - reset password page | Requirements 4.1.10 | Medium
Manage_TConn_34 | On mobile device: iPad 4, the Manage account - reset password page should have a copyright and site version in the footer | Requirements 4.1.2 | Low
Manage_TConn_35 | On mobile device: iPad 4, to ensure that logged users can log off from the Manage account - reset password page | Requirements 4.1.10 | Medium
Manage_TConn_36 | On mobile device: iPhone 6, the Manage account - reset password page should have a copyright and site version in the footer | Requirements 4.1.2 | Low
Manage_TConn_37 | On mobile device: iPhone 6, to ensure that logged users can log off from the Manage account - reset password page | Requirements 4.1.10 | Medium
Manage_TConn_38 | On mobile device: Google Nexus 10, the Manage account - reset password page should have a copyright and site version in the footer | Requirements 4.1.2 | Low
Manage_TConn_39 | On mobile device: Google Nexus 10, to ensure that logged users can log off from the Manage account - reset password page | Requirements 4.1.10 | Medium
Manage_TConn_40 | On mobile device: Samaung Galaxy S4, the Manage account - reset password page should have a copyright and site version in the footer | Requirements 4.1.2 | Low
Manage_TConn_41 | On mobile device: Samaung Galaxy S4, to ensure that logged users can log off from the Manage account - reset password page | Requirements 4.1.10 | Medium
Note on B1: qubsys: Start with : “To show that…” Split the test condition into two parts: “When I do this…this happens…”.

## Test Cases
Test case ID | Objective | Preconditions | Test data | Test condition(s) | Priority | Test completion date | Status | Tester | Defect ID | Defect Status | Defect Severity | Open Date | Close Date | Description / Comment
Manage_TCase_1 | Check if the Company Logo is present in the header of the page | On the Manage Account page | N/A | Manage_TConn_1 | Low | 2015-03-12 | Passed | Chris McClune | [6 empty] | Test Case:
Manage_TCase_2 | Check if the Copyright and site version is available in the footer of the page | On the Manage Account page | N/A | Manage_TConn_2 | Low | 2015-03-12 | Failed | Chris McClune | Defect_Manage_1 | Open | Minor | 2015-03-12 |  | The footer does not contain either the site version or the copyright information |  | “A set of input values, execution pre-conditions, expected results and execution post-conditions, developed for a particular objective or test condition, such as to exercise a particular program path or to verify compliance with a specific requirement.”
Manage_TCase_3 | Check if user input parts of the site have appropriate validation | On the Manage Account page | email: cmcclune02@qub.ac.uk password: validPassword | Manage_TConn_3 | Medium | 2015-03-12 | Failed | Chris McClune | Defect_Manage_2 | Open | Major | 2015-03-12 |  | A password of less that 7 characters can be used, when explicity says 7 or over. |  |  |  | [ISTQB Glossary]
Manage_TCase_4 | Check if the manage account page has a title | On the Manage Account page | N/A | Manage_TConn_4 | Low | 2015-03-17 | Passed | Chris McClune
Manage_TCase_5 | Check if the manage account page is functional | Be logged in and click on email address | email: cmcclune02@qub.ac.uk password: validPassword | Manage_TConn_5 | Medium | 2015-03-17 | Passed | Chris McClune
Manage_TCase_6 | Check if the manage account page has a common navigation area | On the Manage Account page | N/A | Manage_TConn_6 | Medium | 2015-03-17 | Passed | Chris McClune
Manage_TCase_7 | Check if each link in the navigation area works correctly | On the Manage Account page | N/A | Manage_TConn_7 | High | 2015-03-17 | Passed | Chris McClune | [7 empty] | Stats on Test case runs
Manage_TCase_8 | Check if links to the manage account page link works and users can log out from here. | On the Manage Account page | email: cmcclune02@qub.ac.uk password: validPassword | Manage_TConn_8 | High | 2015-03-17 | Passed | Chris McClune | [7 empty] | Passed | 22
Manage_TCase_9 | Check if the user can change their password correctly | On the Manage Account page | current password: validPassword new password: chrisPassword confirm password: chrisPassword | Manage_TConn_9 | High | 2015-03-17 | Passed | Chris McClune | [7 empty] | Failed | 19
Manage_TCase_10 | Check to see if appropriate message is displayed when password is changed | On the Manage Account page | current password: validPassword new password: chrisPassword confirm password: chrisPassword | Manage_TConn_10 | Medium | 2015-03-17 | Failed | Chris McClune | Defect_Manage_3 | Open | Moderate | 2015-03-17 |  | Message displayed is incorrect. Message says username has been changed when password has been changed |  | Not execited | 0
Manage_TCase_11 | Check to see if validation works when changing password | On the Manage Account page | current password: chrisPassword new password: chris confirm password: chris | Manage_TConn_11 | High | 2015-03-17 | Failed | Chris McClune | Defect_Manage_4 | Open | Moderate | 2015-03-17 |  | Password can be changed to something that is 5 characters. Should be at least 7.
Manage_TCase_12 | To test that the manage account page loads correctly on the Amazon Fire 7 inch | Use Amazon Fire 7 inch mobile device | N/A | Manage_TConn_12 | High | 2015-03-17 | Passed | Chris McClune
Manage_TCase_13 | To test if the user can change their password correctly on the Amazon Fire 7 inch | Use Amazon Fire 7 inch mobile device | current password: validPassword new password: chrisPassword confirm password: chrisPassword | Manage_TConn_13 | High | 2015-03-17 | Passed | Chris McClune
Manage_TCase_14 | To test if appropriate message is displayed when changing password on the Amazon Fire 7 inch | Use Amazon Fire 7 inch mobile device | current password: validPassword new password: chrisPassword confirm password: chrisPassword | Manage_TConn_14 | Medium | 2015-03-17 | Failed | Chris McClune | Defect_Manage_5 | Open | Moderate | 2015-03-17 |  | Message displayed is incorrect. Message says username has been changed when password has been changed
Manage_TCase_15 | To test if validation works when changing password using the Amazon Fire 7 inch | Use Amazon Fire 7 inch mobile device | current password: chrisPassword new password: chris confirm password: chris | Manage_TConn_15 | High | 2015-03-17 | Failed | Chris McClune | Defect_Manage_6 | Open | Moderate | 2015-03-17 |  | Password can be changed to something that is 5 characters. Should be at least 7.
Manage_TCase_16 | To test that the manage account page loads correctly on the iPad 4 | Use iPad 4 mobile device | N/A | Manage_TConn_16 | High | 2015-03-17 | Passed | Chris McClune
Manage_TCase_17 | To test if the user can change their password correctly on the iPad 4 | Use iPad 4 mobile device | current password: validPassword new password: chrisPassword confirm password: chrisPassword | Manage_TConn_17 | High | 2015-03-17 | Passed | Chris McClune
Manage_TCase_18 | To test if appropriate message is displayed when changing password on the iPad 4 | Use iPad 4 mobile device | current password: validPassword new password: chrisPassword confirm password: chrisPassword | Manage_TConn_18 | Medium | 2015-03-17 | Failed | Chris McClune | Defect_Manage_7 | Open | Moderate | 2015-03-17 |  | Message displayed is incorrect. Message says username has been changed when password has been changed
Manage_TCase_19 | To test if validation works when changing password using the iPad 4 | Use iPad 4 mobile device | current password: chrisPassword new password: chris confirm password: chris | Manage_TConn_19 | High | 2015-03-17 | Failed | Chris McClune | Defect_Manage_8 | Open | Moderate | 2015-03-17 |  | Password can be changed to something that is 5 characters. Should be at least 7.
Manage_TCase_20 | To test that the manage account page loads correctly on the iPhone 6 | Use iPhone 6 mobile device | N/A | Manage_TConn_20 | High | 2015-03-17 | Passed | Chris McClune
Manage_TCase_21 | To test if the user can change their password correctly on the iPhone 6 | Use iPhone 6 mobile device | current password: validPassword new password: chrisPassword confirm password: chrisPassword | Manage_TConn_21 | High | 2015-03-17 | Passed | Chris McClune
Manage_TCase_22 | To test if appropriate message is displayed when changing password on the iPhone 6 | Use iPhone 6 mobile device | current password: validPassword new password: chrisPassword confirm password: chrisPassword | Manage_TConn_22 | Medium | 2015-03-17 | Failed | Chris McClune | Defect_Manage_9 | Open | Moderate | 2015-03-17 |  | Message displayed is incorrect. Message says username has been changed when password has been changed
Manage_TCase_23 | To test if validation works when changing password using the iPhone 6 | Use iPhone 6 mobile device | current password: chrisPassword new password: chris confirm password: chris | Manage_TConn_23 | High | 2015-03-17 | Failed | Chris McClune | Defect_Manage_10 | Open | Moderate | 2015-03-17 |  | Password can be changed to something that is 5 characters. Should be at least 7.
Manage_TCase_24 | To test that the manage account page loads correctly on the Google Nexus 10 | Use Google Nexus 10 mobile dveice | N/A | Manage_TConn_24 | High | 2015-03-17 | Passed | Chris McClune
Manage_TCase_25 | To test if the user can change their password correctly on the Google Nexus 10 | Use Google Nexus 10 mobile dveice | current password: validPassword new password: chrisPassword confirm password: chrisPassword | Manage_TConn_25 | High | 2015-03-17 | Passed | Chris McClune | [7 empty] | Stats on Defects
Manage_TCase_26 | To test if appropriate message is displayed when changing password on the Google Nexus 10 | Use Google Nexus 10 mobile dveice | current password: validPassword new password: chrisPassword confirm password: chrisPassword | Manage_TConn_26 | Medium | 2015-03-21 | Failed | Chris McClune | Defect_Manage_11 | Open | Moderate | 2015-03-21 |  | Message displayed is incorrect. Message says username has been changed when password has been changed |  | Minor | 1
Manage_TCase_27 | To test if validation works when changing password using the Google Nexus 10 | Use Google Nexus 10 mobile dveice | current password: chrisPassword new password: chris confirm password: chris | Manage_TConn_27 | High | 2015-03-21 | Failed | Chris McClune | Defect_Manage_12 | Open | Moderate | 2015-03-21 |  | Password can be changed to something that is 5 characters. Should be at least 7. |  | Moderate | 0
Manage_TCase_28 | To test that the manage account page loads correctly on the Samsung Galaxy S4 | Use Samsung Galaxy S4 mobile device | N/A | Manage_TConn_28 | High | 2015-03-21 | Passed | Chris McClune | [7 empty] | Major | 1
Manage_TCase_29 | To test if the user can change their password correctly on the Samsung Galaxy S4 | Use Samsung Galaxy S4 mobile device | current password: validPassword new password: chrisPassword confirm password: chrisPassword | Manage_TConn_29 | High | 2015-03-21 | Passed | Chris McClune | [7 empty] | Critical | 0
Manage_TCase_30 | To test if appropriate message is displayed when changing password on the Samsung Galaxy S4 | Use Samsung Galaxy S4 mobile device | current password: validPassword new password: chrisPassword confirm password: chrisPassword | Manage_TConn_30 | Medium | 2015-03-21 | Failed | Chris McClune | Defect_Manage_13 | Open | Moderate | 2015-03-21 |  | Message displayed is incorrect. Message says username has been changed when password has been changed |  | Cosmetic | 0
Manage_TCase_31 | To test if validation works when changing password using the Samsung Galaxy S4 | Use Samsung Galaxy S4 mobile device | current password: chrisPassword new password: chris confirm password: chris | Manage_TConn_31 | High | 2015-03-21 | Failed | Chris McClune | Defect_Manage_14 | Open | Moderate | 2015-03-21 |  | Password can be changed to something that is 5 characters. Should be at least 7.
Manage_TCase_32 | To check if the Manage account - reset password page has a copyright and site version in the footer using the Amazon Fire 7 inch | Logged in and on the Manage Account page | N/A | Manage_TConn_32 | Low | 2015-03-25 | Failed | Chris McClune | Defect_Manage_15 | Open | Cosmetic | 2015-03-25 |  | The footer does not contain either the site version or the copyright information
Manage_TCase_33 | On the Amazon Kindle Fire 7 inch mobile device, to ensure that logged users can log off from the Manage account - reset password page | Logged in and on the Manage Account page | current password: validPassword new password: chrisPassword confirm password: chrisPassword | Manage_TConn_33 | High | 2015-03-25 | Passed | Chris McClune
Manage_TCase_34 | To check if the Manage account - reset password page has a copyright and site version in the footer using the iPad 4 | Logged in and on the Manage Account page | N/A | Manage_TConn_34 | Low | 2015-03-25 | Failed | Chris McClune | Defect_Manage_16 | Open | Cosmetic | 2015-03-25 |  | The footer does not contain either the site version or the copyright information
Manage_TCase_35 | On the Amazon Kindle Fire 7 inch mobile device, to ensure that logged users can log off from the Manage account - reset password page | Logged in and on the Manage Account page | current password: validPassword new password: chrisPassword confirm password: chrisPassword | Manage_TConn_35 | High | 2015-03-25 | Passed | Chris McClune
Manage_TCase_36 | To check if the Manage account - reset password page has a copyright and site version in the footer using the iPhone 6 | Logged in and on the Manage Account page | N/A | Manage_TConn_36 | Low | 2015-03-25 | Failed | Chris McClune | Defect_Manage_17 | Open | Cosmetic | 2015-03-25 |  | The footer does not contain either the site version or the copyright information
Manage_TCase_37 | On the Amazon Kindle Fire 7 inch mobile device, to ensure that logged users can log off from the Manage account - reset password page | Logged in and on the Manage Account page | current password: validPassword new password: chrisPassword confirm password: chrisPassword | Manage_TConn_37 | High | 2015-03-25 | Passed | Chris McClune
Manage_TCase_38 | To check if the Manage account - reset password page has a copyright and site version in the footer using the Google Nexus 10 | Logged in and on the Manage Account page | N/A | Manage_TConn_38 | Low | 2015-03-25 | Failed | Chris McClune | Defect_Manage_18 | Open | Cosmetic | 2015-03-25 |  | The footer does not contain either the site version or the copyright information
Manage_TCase_39 | On the Amazon Kindle Fire 7 inch mobile device, to ensure that logged users can log off from the Manage account - reset password page | Logged in and on the Manage Account page | current password: validPassword new password: chrisPassword confirm password: chrisPassword | Manage_TConn_39 | High | 2015-03-25 | Passed | Chris McClune
Manage_TCase_40 | To check if the Manage account - reset password page has a copyright and site version in the footer using the Samsung Galaxy S4 | Logged in and on the Manage Account page | N/A | Manage_TConn_40 | Low | 2015-03-25 | Failed | Chris McClune | Defect_Manage_19 | Open | Cosmetic | 2015-03-25 |  | The footer does not contain either the site version or the copyright information
Manage_TCase_41 | On the Amazon Kindle Fire 7 inch mobile device, to ensure that logged users can log off from the Manage account - reset password page | Logged in and on the Manage Account page | current password: validPassword new password: chrisPassword confirm password: chrisPassword | Manage_TConn_41 | High | 2015-03-25 | Passed | Chris McClune
Note on A1: qubsys: A unique Identifier for thr Test case
Note on H1: qubsys: The status of the Test case i.e. is it not executed, passed or failed
Note on J1: qubsys: A unique incident ID
Note on K1: qubsys: The status of the defect - initially open but may be moved to reject on review or closed when defect is fixed
Note on L1: qubsys: The assigned severity - Critical: The defect that results in the termination of the complete system or one or more component of the system and causes extensive corruption of the data. The failed function is unusable and there is no acceptable alternative method to achieve the required results then the severity will be stated as critical. Major: The defect that results in the termination of the complete system or one or more component of the system and causes extensive corruption of the data. The failed function is unusable but there exists an acceptable alternative method to achieve the required results then the severity will be stated as major. Moderate: The defect that does not result in the termination, but causes the system to produce incorrect, incomplete or inconsistent results then the severity will be stated as moderate. Minor: The defect that does not result in the termination and does not damage the usability of the system and the desired results can be easily obtained by working around the defects then the severity is stated as minor. Cosmetic: The defect that is related to the enhancement of the system where the changes are related to the look and field of the application then the severity is stated as cosmetic.

## Test Procedures
Test Procedure ID | Test Case ID | Description | Expected Result | Comments | Test Procedure Specification:
Manage_Tproc_1 | Manage_TCase_1 | Go to manage account page and check for the company logo in the header | Company Logo appears in header | Exploratory |  | “A document specifying a sequence of actions for the execution of a test. Also known as test script or manual test script.”
Manage_Tproc_2 | Manage_TCase_2 | Go to manage account page and check for the copyright and version details in the footer | Should see the details in the footer | Exploratory
Manage_Tproc_3 | Manage_TCase_3 | Go to manage account page and change password to something with less than 7 characters | Should not be allowed to change password to this and error message should appear | When the password is changed the prompt says that the username has been changed.
Manage_Tproc_4 | Manage_TCase_4 | Go to the manage account page and check if title is present | Should see title at the top of the page | Exploratory
Manage_Tproc_5 | Manage_TCase_5 | Login to the Pizza IT home page and click on the email address on the top right. | Will be directed to the manage account- reset password page. | Automated Selenium Test
Manage_Tproc_6 | Manage_TCase_6 | Go to the manage account page and check if the common navigation area is present | Should see the common navigatoin area on the page | Exploratory
Manage_Tproc_7 | Manage_TCase_7 | On the manage account page, click on each of the links separately to check that they are working | Should be directed to each page correctly | Automated Selenium Test
Manage_Tproc_8 | Manage_TCase_8
Manage_Tproc_9 | Manage_TCase_9 | On the manage account page enter correct details for the current password and enter a new and confirmed password of at least 7 characters | Should get the appropriate message to say that password has been changed and can use new password to login. | Automated Selenium Test
Manage_Tproc_10 | Manage_TCase_10 | On the manage account page enter correct details for the currecnt password and enter a new and confirmed password of at least 7 characters | Expect to see the appropriate message on screen | Automated Selenium Test
Manage_Tproc_11 | Manage_TCase_11 | Try to change the password on the manage account page using less than 7 characters | Expect to see the validation message on screen | Automated Selenium Test
Manage_Tproc_12 | Manage_TCase_12 | Using an Amazon Fire 7 inch device load the website and login then click on the manage account page | Expect to see website load correctly | Exploratory
Manage_Tproc_13 | Manage_TCase_13 | Using an Amazon Fire 7 inch device, on the manage account page enter correct details for the current password and enter a new and confirmed password of at least 7 characters | Should successfully change the password | Exploratory
Manage_Tproc_14 | Manage_TCase_14 | Using an Amazon Fire 7 inch device, on the manage account page enter correct details for the current password and enter a new and confirmed password of at least 7 characters | Once the password has been changed should see the appropriate message on screen | Exploratory
Manage_Tproc_15 | Manage_TCase_15 | Using an Amazon Fire 7 inch device and try to change the password with less than 7 characters. | The result should show up the validation message to say that the password cannot be changed with less than 7 characters | Exploratory
Manage_Tproc_16 | Manage_TCase_16 | Using an iPad 4 device load the website and login then click on the manage account page | Expect to see website load correctly | Exploratory
Manage_Tproc_17 | Manage_TCase_17 | Using an iPad 4 device, on the manage account page enter correct details for the currecnt password and enter a new and confirmed password of at least 7 characters | Should successfully change the password | Exploratory
Manage_Tproc_18 | Manage_TCase_18 | Using an iPad 4 device, on the manage account page enter correct details for the currecnt password and enter a new and confirmed password of at least 7 characters | Once the password has been changed should see the appropriate message on screen | Exploratory
Manage_Tproc_19 | Manage_TCase_19 | Using an iPad 4 device and try to change the password with less than 7 characters. | The result should show up the validation message to say that the password cannot be changed with less than 7 characters | Exploratory
Manage_Tproc_20 | Manage_TCase_20 | Using an iPhone 6 device load the website and login then click on the manage account page | Expect to see website load correctly | Exploratory
Manage_Tproc_21 | Manage_TCase_21 | Using an iPhone 6 device, on the manage account page enter correct details for the current password and enter a new and confirmed password of at least 7 characters | Should successfully change the password | Exploratory
Manage_Tproc_22 | Manage_TCase_22 | Using an iPhone 6 device, on the manage account page enter correct details for the current password and enter a new and confirmed password of at least 7 characters | Once the password has been changed should see the appropriate message on screen | Exploratory
Manage_Tproc_23 | Manage_TCase_23 | Using an iPhone 6 device and try to change the password with less than 7 characters. | The result should show up the validation message to say that the password cannot be changed with less than 7 characters | Exploratory
Manage_Tproc_24 | Manage_TCase_24 | Using a Google Nexus 10 device load the website and login then click on the manage account page | Expect to see website load correctly | Exploratory
Manage_Tproc_25 | Manage_TCase_25 | Using a Google Nexus 10, on the manage account page enter correct details for the current password and enter a new and confirmed password of at least 7 characters | Should successfully change the password | Exploratory
Manage_Tproc_26 | Manage_TCase_26 | Using a Google Nexus 10, on the manage account page enter correct details for the current password and enter a new and confirmed password of at least 7 characters | Once the password has been changed should see the appropriate message on screen | Exploratory
Manage_Tproc_27 | Manage_TCase_27 | Using an Google Nexus 10 device and try to change the password with less than 7 characters. | The result should show up the validation message to say that the password cannot be changed with less than 7 characters | Exploratory
Manage_Tproc_28 | Manage_TCase_28 | Using a Samsung galaxy S4 device load the website and login then click on the manage account page | Expect to see website load correctly | Exploratory
Manage_Tproc_29 | Manage_TCase_29 | Using a Samsung galaxy S4, on the manage account page enter correct details for the current password and enter a new and confirmed password of at least 7 characters | Should successfully change the password | Exploratory
Manage_Tproc_30 | Manage_TCase_30 | Using a Samsung galaxy S4, on the manage account page enter correct details for the current password and enter a new and confirmed password of at least 7 characters | Once the password has been changed should see the appropriate message on screen | Exploratory
Manage_Tproc_31 | Manage_TCase_31 | Using an Samsung Galaxy S4 device and try to change the password with less than 7 characters. | The result should show up the validation message to say that the password cannot be changed with less than 7 characters | Exploratory
Manage_Tproc_32 | Manage_TCase_32
Manage_Tproc_33 | Manage_TCase_33
Manage_Tproc_34 | Manage_TCase_34
Manage_Tproc_35 | Manage_TCase_35
Manage_Tproc_36 | Manage_TCase_36
Manage_Tproc_37 | Manage_TCase_37
Manage_Tproc_38 | Manage_TCase_38
Manage_Tproc_39 | Manage_TCase_39
Manage_Tproc_40 | Manage_TCase_40
Manage_Tproc_41 | Manage_TCase_41

## Settings
Test status | Test priority | Defect status | Defect Priority
Not executed | High | Closed | Minor
Passed | Medium | Open | Moderate
Failed | Low | Rejected | Major
Critical
Cosmetic