## Reqs
Req | Description
4.1.12 | 4.1.12 The system shall enable registered users to login to using a valid username and password. . The username should be in an email address format and password must be a minimum length six characters.

## Test Conditions
Test Condition ID | Description | Source | Priority
OrderPage_TConn_1 | The Order receipt should include a list of the order items | 4.1.34 | High | What is a test condition?
OrderPage_TConn_2 | The Order receipt should include a list of the order items including extras | 4.1.34 | Medium
OrderPage_TConn_3 | The Order receipt should include a list of the order items including individual prices | 4.1.34 | Medium | •A statement of something we want to test.
OrderPage_TConn_4 | The Order receipt should include the total price | 4.1.34 | Medium | •The required behaviour of the system when that item is used or performed.
OrderPage_TConn_5 | The Order receipt should include the confirmed date and time for collection having selected the now option | 4.1.34 | High | •They enable us to render the requirements and other oracles in such a form that we can understand them and begin to think about how we’re going to test them.
OrderPage_TConn_6 | The Order receipt should include the confirmed date and time for collection having selected the later option for collection | 4.1.34 | High | Test Condition:
OrderPage_TConn_7 | The Order receipt should include the confirmed date and time for collection having selected the later option for collection but choosing a date that has already passed | 4.1.34 | High |  | “An item or event of a component or system that could be verified by one or more test cases, e.g. a function, transaction, feature, quality attribute, or structural element.”
OrderPage_TConn_8 | The Order receipt should include the confirmed date and time for collection having selected the later option for collection but choosing a time that has already passed | 4.1.34 | High
OrderPage_TConn_9 | The Order receipt should include a unique order reference | 4.1.34 | High
OrderPage_TConn_10 | The Order receipt should include a unique order reference different to the test before | 4.1.34 | High
Note on B1: qubsys: Start with : “To show that…” Split the test condition into two parts: “When I do this…this happens…”.

## Test Cases
Test case ID | Objective | Preconditions | Test data | Test condition(s) | Priority | Test completion date | Status | Tester | Defect ID | Defect Status | Defect Severity | Open Date | Close Date | Description / Comment
OrderPage_TCase_1 | To test that the order receipt contains the items placed on order | Have to have already placed an order and selected collection time to see the order receipt | Classic deluxe | OrderPage_TConn_1 | High | 2015-03-11 | Passed | Adam Hale | [6 empty] | Test Case:
OrderPage_TCase_2 | To test that the order receipt contains the items placed on order, specifically looking to see if it records the additional extras | Have to have already placed an order and selected collection time to see the order receipt | Cheese pizza with Olives, Pepperoni, Peppers and Onions as extras | OrderPage_TConn_2 | Medium | 2015-03-11 | Passed | Adam Hale | [7 empty] | “A set of input values, execution pre-conditions, expected results and execution post-conditions, developed for a particular objective or test condition, such as to exercise a particular program path or to verify compliance with a specific requirement.”
OrderPage_TCase_3 | To test that the order receipt contains invididual prices for each item that have been ordered | Have to have already placed an order and selected collection time to see the order receipt | Meat Extravaganza with peppers and onions as extras | OrderPage_TConn_3 | Medium | 2015-03-11 | Failed | Adam Hale | OrderPage_1 | Open | Minor | 2015-03-11 | na | Individual prices are not shown for any item, only the total pricefor the order is. |  |  |  | [ISTQB Glossary]
OrderPage_TCase_4 | To test that the order receipt contains the total price for all items that have been ordered | Have to have already placed an order and selected collection time to see the order receipt | Classic deluxe with olives | OrderPage_TConn_4 | Medium | 2015-03-11 | Passed | Adam Hale
OrderPage_TCase_5 | To test that the order receipt includes the date and time that the order has been placed for collection if selecting to collect now | Have to have already placed an order and selected collection time to see the order receipt | Cheese pizza | OrderPage_TConn_5 | High | 2015-03-11 | Failed | Adam Hale | OrderPage_2 | Open | Moderate | 2015-03-11 | na | This works but it has failed due to the spec clearly saying that the collection time will be 20 minutes after ordering, when it I infact 30 minutes. This has been recorded through the automated Selenium test.
OrderPage_TCase_6 | To test that the order receipt includes the date and time that the order has been placed for collection if selecting to collect later | Have to have already placed an order and selected collection time to see the order receipt | Classic deluxe with pepperoni | OrderPage_TConn_6 | High | 2015-03-11 | Passed | Adam Hale | [7 empty] | Stats on Test case runs
OrderPage_TCase_7 | To test that the system does not progress to the order receipt | Have to have already placed an order and selected collection time to see the order receipt | Classic deluxe with pepperoni | OrderPage_TConn_7 | High | 2015-03-11 | Passed | Adam Hale | [7 empty] | Passed | 7
OrderPage_TCase_8 | To test that the system does not progress to the order receipt | Have to have already placed an order and selected collection time to see the order receipt | Classic deluxe with pepperoni | OrderPage_TConn_8 | High | 2015-03-11 | Passed | Adam Hale | [7 empty] | Failed | 3
OrderPage_TCase_9 | To test that the system provides a unique order reference on the order receipt | Have to have already placed an order and selected collection time to see the order receipt | Meat Extravaganza | OrderPage_TConn_9 | High | 2015-03-11 | Passed | Adam Hale | [7 empty] | Not execited | 0
OrderPage_TCase_10 | To test that the system provides a unique order reference on the order receipt that is different to the previous Test Case | Have to have already placed an order and selected collection time to see the order receipt | Meat Extravaganza with peppers | OrderPage_TConn_10 | High | 2015-03-11 | Failed | Adam Hale | OrderPage_3 | Open | Moderate | 2015-03-11 | na | This is the same order reference as the prevois test case thererfore it is not unique, it is not critical or high as it will not lead to system crash or failure, it will just cause significant difficulties on collection
Stats on Defects
[16 empty] | Minor | 1
[16 empty] | Moderate | 1
[16 empty] | Major | 0
[16 empty] | Critical | 0
[16 empty] | Cosmetic | 0
Note on A1: qubsys: A unique Identifier for thr Test case
Note on H1: qubsys: The status of the Test case i.e. is it not executed, passed or failed
Note on J1: qubsys: A unique incident ID
Note on K1: qubsys: The status of the defect - initially open but may be moved to reject on review or closed when defect is fixed
Note on L1: qubsys: The assigned severity - Critical: The defect that results in the termination of the complete system or one or more component of the system and causes extensive corruption of the data. The failed function is unusable and there is no acceptable alternative method to achieve the required results then the severity will be stated as critical. Major: The defect that results in the termination of the complete system or one or more component of the system and causes extensive corruption of the data. The failed function is unusable but there exists an acceptable alternative method to achieve the required results then the severity will be stated as major. Moderate: The defect that does not result in the termination, but causes the system to produce incorrect, incomplete or inconsistent results then the severity will be stated as moderate. Minor: The defect that does not result in the termination and does not damage the usability of the system and the desired results can be easily obtained by working around the defects then the severity is stated as minor. Cosmetic: The defect that is related to the enhancement of the system where the changes are related to the look and field of the application then the severity is stated as cosmetic.

## Test Procedures
Test Procedure ID | Test Case ID | Description | Expected Result | Comments | Test Procedure Specification:
OrderReceipt_TProc_1 | OrderPage_TConn_1 | Having added an order to the basket with no extras and confirmed the collection time, take user to the order receipt | Order receipt will show item in the receipt | automated selenium test |  | “A document specifying a sequence of actions for the execution of a test. Also known as test script or manual test script.”
OrderReceipt_TProc_2 | OrderPage_TConn_2 | Having added a plain cheese pizza to the basket with Olives, pepperoni, peppers and onions as extras and confirmed the collection time, take user to the order receipt | Order receipt will show item in the receipt alongside the extras selected | automated selenium test
OrderReceipt_TProc_3 | OrderPage_TConn_3 | Having added an order to the basket with extras and confirmed the collection time, take user to the order receipt | Order receipt will show individual prices for each item, including extras, that was ordered | automated selenium test
OrderReceipt_TProc_4 | OrderPage_TConn_4 | Having added an order to the basket with extras and confirmed the collection time, take user to the order receipt | Order receipt will show the total price for all items that have been ordered | automated selenium test
OrderReceipt_TProc_5 | OrderPage_TConn_5 | Having added an order to the basket with no extras and confirmed the collection time as now, take user to the order receipt | Order receipt will show the date and time that the order has been placed for collection | automated selenium test
OrderReceipt_TProc_6 | OrderPage_TConn_6 | Having added an order to the basket with extras and confirmed the collection time as later and selecting when, take user to the order receipt | Order receipt will show the date and time that the order has been placed for collection | automated selenium test
OrderReceipt_TProc_7 | OrderPage_TConn_7 | Having added an order to the basket with extras and confirmed the collection time as later and selecting a date that has passed, that it does not progress to the order receipt | Order receipt will not be generated until valid date is input | automated selenium test
OrderReceipt_TProc_8 | OrderPage_TConn_8 | Having added an order to the basket with extras and confirmed the collection time as later and selecting a time that has passed, that it does not progress to the order receipt | Order receipt will not be generated until valid date is input | automated selenium test
OrderReceipt_TProc_9 | OrderPage_TConn_9 | Having added an order to the basket and confirming valid collection details, the order receipt will have a unique ordering reference on it | Order receipt will have a unique order reference | automated selenium test
OrderReceipt_TProc_10 | OrderPage_TConn_10 | Having added an order to the basket and confirming valid collection details, the order receipt will have a unique ordering reference on it comparing it to the prevoius result | Order receipt will have a unique order reference | automated selenium test

## Settings
Test status | Test priority | Defect status | Defect Priority
Not executed | High | Closed | Minor
Passed | Medium | Open | Moderate
Failed | Low | Rejected | Major
Critical
Cosmetic